## Slide 1: ESG updates (3)
Affect of design change on the NLIS’s project impact performance
Client has issued formal variation order, in respect to the irrigation scope – the drippers part was taken out from the scope of supply
Finolex was requested to submit alternative design for approval. The alternate design will replace drip irrigation with PVC pipe distribution network to supply water at the farm level. The pipes will be used for flooding the farms instead of providing the water to root zone through drip laterals
Change in the project design
Govt. of Karnataka had commissioned Ramthal (Marol) Community Drip Irrigation Project for irrigating 24,000 Ha area in Hungund Taluk
The project has been operational for 2 years and client’s evaluation of the project shows that farmers are not fully able to utilize the drip irrigation technology because
  Lack of awareness about the proper usage and benefits of the technology
  Lack of ownership towards the equipment since it was provided to them free of cost
Flood irrigation method is something which farmers are familiar with and will be able to use effectively, this will be viewed as improvement from conveying the water using canal systems
Reason for change
Finolex has not yet shared full analysis (technical and financial) of the change in the project design therefore on the water
Client will not change the water allocated to the project or the project beneficiary
Status of alternate design proposal

## Slide 2: ESG updates (4)
Affect of design change on the NLIS’s project impact performance
Increased agricultural land under irrigation
Project Benefits and KPI
Drip Irrigation method
Piped Network irrigation method
12,000 ha
12,000 ha
Number of farmers benefitted
12,150
12,150
Reduction in Avg. amount of fertilizer used/ ha
20-50%
No reduction
Increase in yield of major crops
20-100%
Marginal improvement from current practice. The water allocated to the project is as per the drip irrigation method therefore there will be 40-50% shortfall in the water requirement for the crops
Increased water efficiencies in farming
40-50%
No improvement from conventional farming
Increase in income of the farmers
25%
Marginal

## Slide 3: ESG updates (5)
Affect of design change on the NLIS’s project impact performance
Since client will not change the water allocation for the project nor will change the area under irrigation, the water available at farmer will reduce by 40-50% i.e. water will not be sufficient for crops
The entire system will be designed for closed piped network so there may be excess pressure at outlets. Operation and control at the farm level cannot be controlled through SCADA. As pressure and time of application cannot be controlled through system therefore the farmers receiving water at the nighttime will face challenge.
In case of undulations and change in elevation levels, there could be challenge in distributing water equitably
Farmers will not be able to grow multi-crops and neither can change the method of applying fertilizer to the crop
Some of the challenges in changing the design